Project Plan Document

Feeding Scheme Management System

Prepared by: 
Team leader: Olebogeng Phawe - ST10345327

Client Name: Tharimpepe Feeding Scheme

Logo/Icon:

Table of Contents

1. Organisation Overview	3

1.1 Organisation Profile	3

1.2 Business Processes	3

1.3 Stakeholders	3

1.4 System Inputs, Processing and Outputs	4

2. Project Scope, Milestones and Deliverables	4

2.1 Scope of the New System	4

2.2 Risks and Benefits	5

2.3 Milestones and Deliverables	5

3. Work Break Down Structure (WBS)	6

4. Project Schedule (Gantt chart)	7

4.1 Gantt Chart Interpretation	7

5. Risk Management	8

6. Technical Feasibility	10

7. Economic Feasibility	12

8. Team Members	14

9. Appendix	14

10. Reference list	15

​​

​

​

​

​

​

​

​

​

​

​

​

# 1. Organisation Overview

## 1.1 Organisation Profile

Tharimpepe Feeding Scheme is a community-based non-profit organisation located in Mafikeng, North West, South Africa. The organisation focuses on providing daily meals to underprivileged children and vulnerable members of the community.

The feeding scheme operates through donations, volunteer support, and community partnerships. It plays an important role in addressing food insecurity and supporting child development within the local area.

## 1.2 Business Processes

Registration of beneficiaries (children and families) 
Daily meal preparation and distribution 
Recording attendance of beneficiaries 
Tracking food stock and donations 
Managing volunteers and schedules 
Communicating with donors and community stakeholders 
Reporting on feeding activities and impact

## 1.3 Stakeholders

| Stakeholder | Role | Interest in System |
| --- | --- | --- |
| Organisation Manager | Oversees operations and resources | Efficient coordination and reporting |
| Volunteers | Prepare and distribute meals | Clear schedules and task allocation |
| Beneficiaries | Receive meals and support | Reliable and consistent service |
| Donors | Provide food or financial support | Transparency and impact reporting |
| Community Partners | Support outreach initiatives | Organized collaboration |

## 1.4 System Inputs, Processing and Outputs

| Inputs | Processing | Outputs |
| --- | --- | --- |
| Beneficiary details | Registration and record management | Beneficiary lists |
| Attendance records | Daily attendance tracking | Attendance reports |
| Food stock data | Inventory management | Stock level reports |
| Donation records | Donation tracking | Donor reports |
| Volunteer schedules | Task allocation | Volunteer schedules |

# 2. Project Scope, Milestones and Deliverables

## 2.1 Scope of the New System

The project involves developing a web-based Feeding Scheme Management System for Tharimpepe Feeding Scheme.

The system will include:

- Beneficiary registration and management

- Attendance tracking for daily feeding

- Food stock and donation tracking

- Volunteer scheduling

- Reporting and basic analytics

Out of scope:

- Online payment integration

- Mobile application

- Advanced financial accounting

## 2.2 Risks and Benefits

Risks

- Continued reliance on manual processes leading to data errors

- Delays in development affecting implementation

- Limited access to accurate records

Benefits

- Improved organisation and efficiency

- Better tracking of beneficiaries and resources

- Enhanced transparency for donors

- Reduced administrative workload

## 2.3 Milestones and Deliverables

| # | Milestone | Deliverable | Target |
| --- | --- | --- | --- |
| 1 | Planning Complete | Project Plan | Week 2 |
| 2 | Analysis Complete | Requirements & Diagrams | Week 4 |
| 3 | Design Complete | ERD & UI Designs | Week 7 |
| 4 | Development Complete | Working System | Week 11 |
| 5 | Testing Complete | Test Results | Week 13 |
| 6 | Handover Complete | Final System & Presentation | Week 15 |

# 3. Work Break Down Structure (WBS)

| ID | Task | Duration | Assigned |
| --- | --- | --- | --- |
| 1 | Project Initiation | 1 week | Both |
| 2 | Requirements Gathering | 1 week | Student B |
| 3 | System Analysis | 2 weeks | Both |
| 4 | Project Planning | 1 week | Student A |
| 5 | Database Design | 2 weeks | Student A |
| 6 | UI Design | 2 weeks | Student B |
| 7 | Backend Development | 3 weeks | Student A |
| 8 | Frontend Development | 3 weeks | Student B |
| 9 | Integration | 1 week | Both |
| 10 | Testing | 1 week | Both |
| 11 | Documentation | 1 week | Student B |
| 12 | Presentation | 1 week | Both |

Figure 1: Gantt chart created in TeamGantt

4. Project Schedule (Gantt chart)

## 4.1 Gantt Chart Interpretation

- Weeks 1–2 (Initiation & Planning): Tasks 1, 2, and 4 are executed in parallel to establish the project foundation, define scope, and produce the initial project plan documentation. This parallel execution reduces the setup time and accelerates project readiness.

- Weeks 3–6 (Analysis & Design): System analysis (Task 3) is completed first and serves as an input for the design phase. Thereafter, two tasks run concurrently: database design (Task 5) handled by Student A, and user interface design (Task 6) handled by Student B. This parallel structure improves efficiency and optimizes resource utilization.

- Weeks 7–9 (Development): Backend development (Task 7) and frontend development (Task 8) are carried out simultaneously by different team members. This overlap reduces the total development duration from a potential 6 weeks to 3 weeks, improving overall project efficiency.

- Weeks 10–15 (Integration, Testing, Documentation, Presentation): These tasks are performed sequentially: integration (Task 9), testing (Task 10), documentation (Task 11), and final presentation and handover (Task 12). This structured sequence ensures that each phase is validated before progressing, maintaining quality and reducing risk.

- Critical Path: Task 1 → Task 2 → Task 3 → Task 5 → Task 7 → Task 9 → Task 10 → Task 11 → Task 12. This represents the longest chain of dependent tasks and determines the minimum project duration of 15 weeks. Any delay in these tasks will directly impact the overall project completion time.

# 5. Risk Management

Risk Identification and Analysis: We extend the original risk list by adding several threats. For example, data security breach (compromise of beneficiary data) is a Medium-probability/High-impact risk that requires encryption, secure hosting and incident-response procedures (Contingency: restore from backups). Power or Internet outages (common in the region) are High-probability/Medium-impact risks; mitigation includes UPS/battery backups and offline-capable data entry, with contingency of manual logs until service returns. Volunteer/Staff unavailability (e.g. illness or drop-out) is assessed as Medium/Medium; mitigation involves cross-training and backup volunteers. Scope creep (new requirements introduced mid-project) is Medium/High; strict change-control and documented approvals are mitigation, with contingency to defer non-essential features. Each risk was assessed by likelihood and impact and placed on a risk matrix, following PMI best practices (Staman 2004).

| Risk | Probability | Impact | Mitigation | Contingency |
| --- | --- | --- | --- | --- |
| Team member unavailable (e.g. illness) | Medium | High | Task redistribution; shared documentation; Git version control (reduces single-point failure) | Backup personnel; use handover docs |
| Lack of stakeholder input | Low | High | Regular meetings and communications with donors and volunteers; clear reports on needs (ensures engagement) | Provide status updates; conduct surveys |
| Schedule delays | Medium | High | Weekly progress reviews; buffer time in schedule; early detection of slippage | Re-plan timeline; reassign resources |
| Technical challenges (bugs, bugs) | Low | Medium | Code reviews; use of proven libraries; prototyping (reduces uncertainty) | Allocate extra testing/debug hours |
| Data security breach | Medium | High | SSL/TLS encryption; strong authentication; secure hosting (minimises risk) | Incident response plan; data recovery from backups |
| Power/Internet outage | High | Medium | Install UPS/batteries; design offline data entry (service workers/PWA) | Manual forms; sync data later |
| Volunteer dropout | Medium | Medium | Maintain volunteer pool; schedule overlap; automated reminders | Use community volunteers; reschedule if needed |
| Scope creep (requirements change) | Medium | High | Freeze scope after sign-off; formal change control (prevents uncontrolled growth) | Defer new features to later phase; negotiate timeline |
| Funding shortfall or donor delay | Low | Medium | Use free/open-source tools (Daly 2019) and open grants; minimal hardware needs | Reduce non-critical features; seek alternative funding |

Risk Heatmap (Probability vs Impact):

| Risk | Owner | Trigger/Indicator | Review Frequency |
| --- | --- | --- | --- |
| Data breach | Dev Lead | Unauthorized access detected | Weekly review or immediately on alert |
| Volunteer dropout | Team Leader | Notice of resignation/no-show | Weekly team meeting |
| Power/Internet outage | Team Leader | Local outage report | After each outage; weekly uptime check |
| Scope change request | Team Leader | New feature request | Each stakeholder review |
| Funding shortfall | Team Leader | Funding delay notice | Monthly budget review |

Risk Monitoring Plan: Each risk has an assigned owner, trigger, and review frequency as follows

| Risk | Owner | Trigger/Indicator | Review Frequency |
| --- | --- | --- | --- |
| Data breach | Dev Lead | Unauthorized access detected | Weekly review or immediately on alert |
| Volunteer dropout | Team Leader | Notice of resignation/no-show | Weekly team meeting |
| Power/Internet outage | Team Leader | Local outage report | After each outage; weekly uptime check |
| Scope change request | Team Leader | New feature request | Each stakeholder review |
| Funding shortfall | Team Leader | Funding delay notice | Monthly budget review |

# 6. Technical Feasibility

- Hardware Requirements: Technical feasibility requires verifying that necessary hardware is (or can be) procured. For this project, development laptops must meet recommended web-development specs: at least 8 GB RAM, Intel i5 (or equivalent) CPU and 256 GB SSD storage

These thresholds are advised by web-development educators (Arola 2022) and ensure smooth IDE/db operations. We assume existing laptops meet or exceed these. Network connectivity should be reliable broadband (e.g. 10+ Mbps); in practice, South African NGOs may experience outages, so a backup mobile data plan or offline design is recommended. Server/Hosting needs are modest: a simple Linux web server with ~2 GB RAM and 20 GB disk (which is available on free-tier cloud platforms). We assume costs for any new hosting (e.g. AWS free tier) are negligible.

- Software Requirements: All required software has free options. We will use Visual Studio Code (free IDE), MySQL via XAMPP (free LAMP stack) for the database, and Git/GitHub (free for private repos) for version control. Figma (free tier) or similar can be used for UI mock-ups. Office tasks can use LibreOffice (open-source) to avoid licensing costs (Daly 2019). Microsoft Project can be replaced by free Gantt tools (e.g. GanttProject). This adheres to best practice of utilising open-source solutions for NGOs to minimize costs (Daly 2019).

- Constraints & Solutions: The main technical constraints are connectivity and power reliability. To mitigate these, the web app should support an offline mode (for example via Progressive Web App technologies, caching key forms) so that meal counts and data can be entered offline and synced later. Local data backups (e.g. weekly exports to USB drive) and a UPS for any local server mitigate hardware failure. We also assume that essential expertise (for LAMP and PHP development) is available in the team or via consultants (as per feasibility check practices (Cyfersoft 2025)).

- Deployment Checklist: Table 1 below outlines key deployment tasks and estimated durations. Using a checklist is recommended to minimize mistakes and vulnerabilities during deployment (Syncro 2025). Each task can be done sequentially or in parallel as noted.

| Task | Owner | Duration | Dependencies |
| --- | --- | --- | --- |
| Prepare Hardware & Access | Team Leader | 1 day | – |
| Verify laptops meet specs, install OS updates | Devs |  |  |
| Ensure internet/UPS/battery backup ready | IT Support |  |  |
| Setup Development Environment | Dev Team | 2 days | Hardware ready |
| Install IDE (VS Code), XAMPP, Git | Devs |  |  |
| Configure local database (MySQL) | Devs |  |  |
| Provision Hosting Environment | DevOps/IT | 2 days | – |
| Create cloud instance (or configure on-site server) |  |  |  |
| Install web server and DB on server | IT Support |  |  |
| Deploy Initial Application Code | Dev Team | 2 days | Environment set up |
| Commit & push code to server | Devs |  |  |
| Run migrations/seed data | Devs |  |  |
| Configure Backups & Security | IT Support | 1 day | Hosting set up |
| Schedule automated DB dumps (e.g. daily to cloud) | IT |  |  |
| Configure SSL certificate, firewall rules | IT Support |  |  |
| Testing & Launch | Team Leader | 2 days | All above |
| Functional/integration testing | QA Team |  |  |
| Final adjustments, user training | All |  |  |

# 7. Economic Feasibility

Cost Estimation Method: We base cost estimates on the Work Breakdown Structure, ensuring 100% of the scope is covered (Malsam 2024). Each task’s duration (in weeks) and effort (hours) are computed, assuming 40 hours/week per person. We then apply an hourly rate of R65/h (approximate local junior developer rate). Table 2 below shows this breakdown. Multi-person tasks (e.g. integration) assume parallel effort. Our totals are compared with the given R47,040.

| WBS ID | Task | Duration (weeks) | Effort (hours) | Hourly Rate (R) | Cost (R) |
| --- | --- | --- | --- | --- | --- |
| 1 | Project Initiation | 1 | 80 | 65 | 5,200 |
| 2 | Requirements Gathering | 1 | 40 | 65 | 2,600 |
| 3 | System Analysis | 2 | 80 | 65 | 5,200 |
| 4 | Project Planning | 1 | 40 | 65 | 2,600 |
| 5 | Database Design | 2 | 80 | 65 | 5,200 |
| 6 | UI Design | 2 | 80 | 65 | 5,200 |
| 7 | Backend Development | 3 | 120 | 65 | 7,800 |
| 8 | Frontend Development | 3 | 120 | 65 | 7,800 |
| 9 | Integration | 1 | 80 | 65 | 5,200 |
| 10 | Testing | 1 | 80 | 65 | 5,200 |
| 11 | Documentation | 1 | 40 | 65 | 2,600 |
| 12 | Presentation & Handover | 1 | 80 | 65 | 5,200 |
|  | Total | 15 | 960 |  | 62,400 |

Table 1:  Effort-based cost estimate. “Effort” accounts for 2-person tasks (e.g. 80h for task 1 means 2×40h). Total cost = R62,400.

Our total (R62,400) exceeds the stated R47,040. The discrepancy may arise from conservative assumptions (e.g. all tasks at full two-person effort). If we assume some tasks run sequentially rather than in parallel, or a lower effective rate, costs align more closely. For instance, using 720 total hours (as a streamlined plan) yields R46,800 (720×65), nearly R47,040.

Sensitivity Analysis: We consider cost variations:

- +10% labour: If actual hours are 10% higher (1,056 h), cost = R68,640.

- +20% contingency: If we add 20% contingency on base cost (R62,400×1.20), cost = R74,880.

Even with these buffers, the project remains feasible given expected grant funding; these scenarios allow planning for overruns.

Assumptions: Key assumptions include a 2-person team at 40 h/week, an hourly rate of R65, no major licensing or hardware purchases (per project scope), and that tasks can be partly overlapped. All software tools (development IDE, database, design tools) are free or already owned. Hosting is assumed free or minimal (e.g. cloud free-tier). Any unspecified items (e.g. exact hosting provider or transport costs) are assumed negligible or covered by existing resources.

# 8. Team Members

| Team Leader | Team member |
| --- | --- |
| Description: | Description: |

# 9. Appendix

- Tharimpepe Logo:

Tharimpepe Facebook link: https://www.facebook.com/profile.php?id=100083976069889

# 10. Reference list

Arola, M. (2022) Hardware Requirements for Web Development Bootcamps, Nashville Software School [online] available at: https://learn.nashvillesoftwareschool.com/blog/  (Accessed March 2026).

Daly, R. (2019) The pros and cons of switching to free and open-source digital tools and software, CultureHive [online] available at: https://www.culturehive.co.uk  (Accessed April 2026).

Malsam, W. (2024) Project Management Best Practices: WBS, Risk, and Scheduling, ProjectManager.com [online] available at: https://www.projectmanager.com/blog  (Accessed March 2026).

Staman, O.D. (2004) “Clear skies: With focused brainstorming and a comprehensive plan, project managers with the U.S. Air Force avoided risks”, PM Network, 18(3), pp.40–46.

SyncroSecure (2025) Software Deployment Checklist: A Guide for IT Professionals, Syncro blog [online] available at: https://syncrosecure.com/blog  (Accessed March 2026).